## TestCaseTemplate
Test Case Template
TestCaseId | Component | Priority | Description/Test Summary | Pre-requisites | Test Steps | Expected Result | Actual Result | Status | Test Executed By
AdminCreation_1 | User_Creation_Module | P0 | Verify that when an Admin attempts to create a new administrative account with valid info, account creation is successful. | On admin landing page | 1. Select create new user. 2. Verify that "Administrative account" is selectable from account type drop down menu. 3. Enter valid information. 4. Create new user. 5. Verify account creation is successful by logging into newly made account. | Admin login is successful using new account and account is on administrative landing page. | Admin login is successful using new account and account is on administrative landing page. | Pass | Zhang
AdminCreation_2 | User_Creation_Module | P0 | Verify that when an Admin attempts to create a new administrative account with INVALID information, page refreshes and highlights section with invalid information. | On admin landing page | 1. Select create new user. 2. Verify that "Administrative account" is selectable from account type drop down menu. 3. Enter INVALID information. 4. Create new user. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | Pass | Zhang
AdminCreation_3 | User_Creation_Module | P0 | Verify that when a librarian attempts to create a new account, "Administrative account" is not visible form the account type drop down menu. | On librarian landing page | 1. Select create new user. 2. Verify that "Administrative account" is not selectable from account type drop down menu. | No "Administrative account" option is selectable in the account type menu on user creation page | No "Administrative account" option is selectable in the account type menu on user creation page | Pass | Zhang
LibrarianCreation_1 | User_Creation_Module | P0 | Verify that when ANY Admin attempts to create a new librarian account with valid info, account creation is successful. | On admin landing page | 1. Select create new user. 2. Verify that "Librarian account" is selectable from account type drop down menu. 3. Enter valid information. 4. Create new user. 5. Verify account creation is successful by logging into newly made account. | Librarian login is successful using new account and account is on librarian landing page. | New librarian account was not added to the database resulting in a failed login attempt. | Fail | Han
LibrarianCreation_2 | User_Creation_Module | P0 | Verify that when ANY Admin attempts to create a new librarian account with INVALID information, page refreshes and highlights section with invalid information. | On admin landing page | 1. Select create new user. 2. Verify that "Librarian account" is selectable from account type drop down menu. 3. Enter INVALID information. 4. Create new user. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | Pass | Han
LibrarianCreation_3 | User_Creation_Module | P0 | Verify that a librarian account cannot make another librarian account | On librarian landing page | 1. Select create new user. 2. Verify that "Librarian account" is not selectable from account type drop down menu. | No "Librarian account" option is selectable in the account type menu on user creation page | No "Librarian account" option is selectable in the account type menu on user creation page | Pass | Han
UserCreation_1 | User_Creation_Module | P0 | Verify that when ANY Admin OR Librarian attempts to create a new user account with valid info, account creation is successful. | On admin OR librarian landing page | 1. Select create new user. 2. Verify that "User account" is selectable from account type drop down menu. 3. Enter valid information. 4. Create new user. 5. Verify account creation is successful by logging into newly made account. | User login is successful using new account and account is on user landing page. | User login is successful using new account and account is on user landing page. | Pass | Reyes
UserCreation_2 | User_Creation_Module | P0 | Verify that when ANY admin OR librarian attempts to create a new user account with INVALID information, page refreshes and highlights section with invalid information. | On admin OR librarian landing page | 1. Select create new user. 2. Verify that "User account" is selectable from account type drop down menu. 3. Enter INVALID information. 4. Create new user. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | User creation page should refresh and highlight field with invalid information, along with an associated error message. | Pass | Reyes
UserCreation_3 | User_Creation_Module | P0 | Verify that a user account cannot make another librarian account | On user landing page | 1. Verify there is no "user creation" button on the landing page. | No "user creation" button on landing page. | No "user creation" button on landing page. | Pass | Reyes
UserLogin_1 | Login_Module | P0 | Verify that when a user enters the CORRECT username and password, that they are redirected to the ADMIN landing page. | Application is launched | 1. Enter an ADMIN username 2. Enter password 3. Click login button or press enter | User login is successful and is redireected to the admin landing page | User login is successful and is redireected to the admin landing page | Pass | Reyes
UserLogin_2 | Login_Module | P0 | Verify that when a user enters the CORRECT username and password, that they are redirected to the LIBRARIAN landing page. | Application is launched | 1. Enter a LIBRARIAN username 2. Enter password 3. Click login button or press enter | User login is successful and is redireected to the librarian landing page | User login is successful and is redireected to the librarian landing page | Pass | Reyes
UserLogin_3 | Login_Module | P0 | Verify that when a user enters the CORRECT username and password, that they are redirected to the USER landing page. | Application is launched | 1. Enter a USER username 2. Enter password 3. Click login button or press enter | User login is successful and is redireected to the user landing page | User login is successful and is redireected to the user landing page | Pass | Reyes
UserLogin_4 | Login_Module | P0 | Verify that when a user enters the INCORRECT username, page refreshes, shows "INVALID LOGIN" error above username field and allows the user to retry. | Application is launched | 1. Enter INCORRECT username 2. Enter any password 3. Click login button or press enter | User login is unsuccessful and page reloads to show "INVALID LOGIN" above login module. | User login is unsuccessful and page reloads to show "INVALID LOGIN" above login module. | Pass | Reyes
UserLogin_5 | Login_Module | P0 | Verify that when a user enters the CORRECT username but INVALID password, page refreshes, shows "INVALID LOGIN" error above username field and allows the user to retry. | Application is launched | 1. Enter a valid username 2. Enter an INCORRECT password 3. Click login button or press enter | User login is unsuccessful and page reloads to show "INVALID LOGIN" above login module. | User login is unsuccessful and page reloads to show "INVALID LOGIN" above login module. | Pass | Reyes
BookReturn_1 | Reservations_and_Hold_Management | P1 | Verify that when a user returns a book on time, the book status is updated as "Pending Return Processing" | On admin/librarian landing page | 1. Click the "Reservations and Holds" button. 2. Scan User ID Barcode or enter User ID Number in user field. 3. Scan book barcode or enter barcode number in book field. 4. Verify the details page brings up the correct book. 5. Verify there is no late return notification. 6. Click confirm return. | Status of the book changes from "Checked Out to "Pending Return Processing". | Status of the book changes from "Checked Out to "Pending Return Processing". | Pass | Han
BookReturn_2 | Reservations_and_Hold_Management | P1 | Verify that when a user returns a book LATE, an account hold is made, librarian and user are notified and the book status is updated as "Pending Return Processing" | On admin/librarian landing page | 1. Click the "Reservations and Holds" button. 2. Scan User ID Barcode or enter User ID Number in user field. 3. Scan book barcode or enter barcode number in book field. 4. Verify the details page brings up the correct book. 5. Verify there is a late return notification window. 6. Click the close button in the notification window. 7. Verify User Information panel blinks red. 8.. Click confirm return. | Late Return Notification window pops up, User status has changed to "Hold on Record", the correct late fee is applied to the User account page, and status of the book changes from "Checked Out to "Pending Return Processing". | Late Return Notification window pops up, User status has changed to "Hold on Record", the correct late fee is applied to the User account page, and status of the book changes from "Checked Out to "Pending Return Processing". | Pass | Han
BookReturn_3 | Reservations_and_Hold_Management | P1 | Verify that when a user attempts to return a book that is not valid in the system, a "invalid book code" notification pops up. | On admin/librarian landing page | 1. Click the "Reservations and Holds" button. 2. Scan User ID Barcode or enter User ID Number in user field. 3. Scan book barcode or enter barcode number in book field. 4. Verify an "invalid book code" notification pops up. 5. Click close button on nitofication window. | "Invalid Book Code" notifcation window pops up and closes upon clicking the close button. | "Invalid Book Code" notifcation window pops up and closes upon clicking the close button. | Pass | Han
BooksReservation_1 | Reservations_and_Hold_Management | P1 | Verifys that a user can reserve an available book . Then update to the database that book has been reserved. | On user landing page | 1. Login in a valid user account. 2. Go into the book search bar, and search for desired book. 3. After the book is found, then click on the reserve button. 4. Librarians will be alerted to the reservation and will approve the reservation. 5. Database updates that the reservation was successful. | Page should automatically redirected to an another page that would show that the reservation was success. | Page should automatically redirected to an another page that would show that the reservation was success. | Pass | Han
BooksReservation_2 | Reservations_and_Hold_Management | P1 | Verify that a user unable reserve an unavailable book. | On user landing page | 1. Login in a valid user account. 2. Go into the book search bar, and search for desired book. 3. After the book is found, then click on the reserve button. 4. "Unavailable book" window pops up. 5. Click close button on the window. | "Unavailable book" window shows up to inform that the book is unavailable. Closes upon clicking the close window. | "Unavailable book" window shows up to inform that the book is unavailable. Closes upon clicking the close window. | Pass | Han
PaymentFee_1 | Payment_Services_System | P2 | Verify that user had paid for a fee with a valid method of payment. | On user landing page | 1. Login in a valid user account 2. Select "Payment and Fees" button 3. Select "Pay now" button 4. Selected payment method and input valid information to pay. 5. Database updates that payment was successful. | Page should automatically redirected to an another page that shows that payment was succcessful. | Page should automatically redirected to an another page that shows that payment was succcessful. | Pass | Zhang
PaymentFee_2 | Payment_Services_System | P2 | Verifys that when user attempts to pay a fee with a INVALID method of payment. The payment will be rejected and user will be prompt to try again. | On user landing page | 1. Login in a valid user account 2. Select "Payment and Fees" button 3. Select "Pay now" button 4. Selected payment method and input INVALID information to pay. 5. Payment will then be reject and user would be prompt to try again. | "Invalid payment information", notificaiton window pops up and closes upon clicking the close button | "Invalid payment information", notificaiton window pops up and closes upon clicking the close button | Pass | Zhang
AddBook_1 | Library_Catalog_Module | P3 | Verifys that a book is added in the database with unnecessary and necessary information. | On librarian landing page | 1. Login in a valid librarian user account. 2. Librarian selects add book button 3. Librarian fills out all information about the book. 4.Database updates that the book has been added in. | Page should automatically redirect to another page to show that books has been added successfully. | Page should automatically redirect to another page to show that books has been added successfully. | Pass | Zhang
AddBook_2 | Library_Catalog_Module | P3 | Verifys that a book is added in the database with only the neccessary information | On librarian landing page | 1. Login in a valid librarian user account. 2. Librarian selects add book button 3. Librarian fills out only the necessary information about the book. 4. Database updates that the book has been added with only the necessary information. | Page should automatically redirect to another page to show that books has been added successfully. | Page should automatically redirect to another page to show that books has been added successfully. | Pass | Zhang
AddBook_3 | Library_Catalog_Module | P3 | Verifys that a book can not added in the database with none of the neccessary information | On librarian landing page | 1. Login in a valid librarian user account. 2. Librarian selects add book button 3. Librarian tries to continue without putting any information. 4. "Invalid submition" window pops and prohbits the book from being added into the database and missing necessary information will be highlighted. | "Invalid submition" windows pops up and prompts the librarian to input the necessary information. | "Invalid submition" windows pops up and prompts the librarian to input the necessary information. | Pass | Zhang
BookSearch_1 | DDS_Search_Bar | P3 | Verifty that when a user scans or provides a VALID barcode, this leads to the details page of the book. | On librarian landing page | 1. Scan barcode or enter applicable barcode entry. | Page should automatically redirect once required character count is reached to the applicable book details page | Page should automatically redirect once required character count is reached to the applicable book details page | Pass | Zhang
BookSearch_2 | DDS_Search_Bar | P3 | Verifty that when a user scans or provides a INVALID barcode, this leads to the invalid barcode page. | On librarian landing page | 1. Scan INVALID barcode or enter INVALID barcode entry. | Page should automatically redirect once required character count is reached to the INVALID barcode page. | Page redirected to last scanned book | Fail | Zhang